## Project charter
PROJECT CHARTER
PROJECT NAME | ColorGlasses | SPONSOR | Camaleon Inc.
PROJECT MANAGER | Fariba | DEPARTMENT | product R&D
PROJECT PRESENTATION
CONTEXT AND JUSTIFICATION
In 2025, there is a growing demand for technological fashion, particularly in eyewear. Consumers increasingly seek products that are both functional and stylish, with a focus on fashion-tech innovation. The development of color-changing smart glasses aligns with market trends, as it provides a customizable and innovative accessory. By using existing advancements in smart materials, the project aims to be the first to market with a groundbreaking product.
GOAL OF THE PROJECT
To create glasses that can change color to match outfits and personal preferences, merging existing smart material technology with fashion innovation.
SUCCESS CRITERIA
To create innovative glasses that can change color based on the wearer’s outfit and personal preferences, incorporating advanced technology into fashion.
OBJECTIVES OF THE PROJECT |  | KPIs
Be the first to market with color-changing glasses |  | Achieve a product release date within the agreed timeline
Incorporate the new color changing material in our lenses |  | Gather at least 80% positive feedback on color options in user testing.
Design and implement a mobile app for glasses control |  | Demonstrate advanced features in prototypes
Establish a default color palette for the glasses
developing special features for lenses
PERIMETER
WITHIN SCOPE |  | OUT OF SCOPE
Design and development of the mobile application or platform that controls the color change |  | Development of prescription lenses or AR functionality
Creating a set of default color palettes for users |  | Support for third-party fashion apps
Ensuring durability and user-friendliness of the glasses |  | Long-term maintenance or repair services
Integration of pre-developed smart material into glasses design |  | Custom user-generated colors outside initial app scope
DELIVERABLES
Functional prototype of color-changing glasses
Mobile app for color control
User manual with setup and usage instructions
Final R&D documentation for product integration and testing results
STAKEHOLDERS AND PROJECT ORGANISATION
NAME | ROLE |  | TEAM
Fariba | Project Manager |  | Steering Committee
Fariba | President |  | Steering Committee
Google/Meta Executive | Sponsor |  | Steering Committee
Fariba | Product designer |  | Core Team
Gerard | Mobile App Developer |  | Core Team
David | Hardware Engineer |  | Core Team
David | Marketing Specialist |  | Core Team
PLAN
MILESTONE |  |  | DATE
Completion of material reserch |  |  | Januray 15,2025
Prototype development |  |  | April 4, 2025
App design and testing |  |  | July 25, 2025
Final product adjustments |  |  | September 19, 2025
App design and testing |  |  | May 16, 2025
Product launch |  |  | October 17, 2025
RISK FACTORS
ASSUMPTIONS |  | DEPENDENCIES
Availability of advanced smart material for lenses |  | Partnerships with material suppliers
Existnig team expertis in app and material design |  | Successful integration of app and glasses technology
High consumer interest in technologically enhanced fashion products |  | Timely feedback from user testing
CONSTRAINTS |  | RISKS
Budget limitations for research and app development |  | Technical challenges in material development
Tight timeline to be the first to market |  | App bugs affecting user experience
Competition from rival brands developing similar products
Competition from rival brands.
BUDGET
WORKLOAD ESTIMATION |  | OTHER COSTS
Materials/Hardware Team: 500 hours |  | Material costs: $50,000
App Development Team: 400 hours |  | App development software/tools: $20,000
Design Team: 200 hours |  | Marketing and launch campaigns: $30,000
Testing Team: 200 hours |  | Testing and feedback sessions: $15,000

## RACI
WBS ID | Task Name | Steering Committee | Core Team | Sponsor | Project Manager | Product Designer | Hardware Engineer | App Developer | Marketing Specialist | Testers
ID1.1 | Project Kickoff | A | R | C | R | I | I | I | I | -
ID1.2 | Market Research | C | C | I | A | R | - | - | R | -
ID1.3 | Project Charter | C | C | A | R | I | I | I | I | -
ID2.1 | Product Design Specifications | C | C | I | A | R | R | C | - | -
ID2.2 | App Interface Design | I | C | I | A | R | - | R | C | -
ID3.1 | Hardware Prototyping | I | C | I | A | C | R | - | - | -
ID3.2 | App Development | I | C | I | A | C | - | R | - | -
ID3.3 | Bluetooth-Glasses Integration | I | C | I | A | C | R | R | - | -
ID4.1 | Recruit Testers | - | C | I | A | - | - | - | R | C
ID4.2 | User Testing | I | C | I | A | C | C | C | - | R
ID4.3 | Feedback Analysis | I | C | I | A | R | R | R | C | C
ID5.1 | Pre-launch Campaign | I | C | C | A | C | - | - | R | -
ID5.2 | Social Media Outreach | I | C | I | A | - | - | - | R | -
ID6.1 | Final Product Adjustments | I | C | I | A | R | R | R | - | C
ID6.2 | Final Testing | I | C | I | A | C | R | R | - | R
ID6.3 | Launch Preparations | I | C | C | A | C | C | C | R | -
R | Responsible
A | Accountable
C | Consulted
I | Informed

## Gantt
https://www.wrike.com/workspace.htm?acc=6622171#/folder/1530465110/timeline3?viewId=322863534
Exported Table from Wrike:
Key | Folder | Parent task | Default task workflow | Default project workflow | Title | Workflow | Status | Custom status | Priority | Assigned To | Start Date | Duration | Duration (Hours) | Effort | Time Spent (Hours) | End Date | Depends On | Start Date Constraint | Description | Budget | Impact
1 | / |  |  |  | Project Initiation | Default Workflow | Active | New | Normal |  | 2025-01-06 | 20 days | 1900-01-05 16:00 |  |  | 2025-01-31
2 | / | Project Initiation |  |  | Project Kickoff | Default Workflow | Active | New | High |  | 2025-01-06 | 5 days | 1899-12-31 16:00 |  |  | 2025-01-10
3 | / | Project Initiation |  |  | Market Research | Default Workflow | Active | New | Normal |  | 2025-01-13 | 10 days | 1900-01-02 08:00 |  |  | 2025-01-24 | 2FS
4 | / | Project Initiation |  |  | Project Charter | Default Workflow | Active | New | High |  | 2025-01-27 | 5 days | 1899-12-31 16:00 |  |  | 2025-01-31 | 3FS
5 | / |  |  |  | Design Phase | Default Workflow | Active | New | Normal |  | 2025-02-03 | 15 days | 1900-01-04 |  |  | 2025-02-21
6 | / | Design Phase |  |  | Product Design Specifications | Default Workflow | Active | New | High |  | 2025-02-03 | 15 days | 1900-01-04 |  |  | 2025-02-21 | 4FS
7 | / | Design Phase |  |  | App Interface Design | Default Workflow | Active | New | High |  | 2025-02-03 | 15 days | 1900-01-04 |  |  | 2025-02-21 | 4FS
8 | / |  |  |  | Development Phase | Default Workflow | Active | New | Normal |  | 2025-02-24 | 45 days | 1900-01-14 |  |  | 2025-04-25
9 | / | Development Phase |  |  | Hardware Prototyping | Default Workflow | Active | New | High |  | 2025-02-24 | 20 days | 1900-01-05 16:00 |  |  | 2025-03-21 | 6FS
10 | / | Development Phase |  |  | App Development | Default Workflow | Active | New | High |  | 2025-02-24 | 30 days | 1900-01-09 |  |  | 2025-04-04 | 7FS
11 | / | Development Phase |  |  | Bluetooth Integration | Default Workflow | Active | New | High |  | 2025-04-07 | 15 days | 1900-01-04 |  |  | 2025-04-25 | 10FS
12 | / |  |  |  | Testing Phase | Default Workflow | Active | New | Normal |  | 2025-04-07 | 35 days | 1900-01-10 16:00 |  |  | 2025-05-23
13 | / | Testing Phase |  |  | Recruit Testers | Default Workflow | Active | New | Normal |  | 2025-04-07 | 10 days | 1900-01-02 08:00 |  |  | 2025-04-18 | 10FS
14 | / | Testing Phase |  |  | User Testing | Default Workflow | Active | New | High |  | 2025-04-21 | 15 days | 1900-01-04 |  |  | 2025-05-09 | 13FS
15 | / | Testing Phase |  |  | Feedback Analysis | Default Workflow | Active | New | Normal |  | 2025-05-12 | 10 days | 1900-01-02 08:00 |  |  | 2025-05-23 | 14FS
16 | / |  |  |  | Marketing Phase | Default Workflow | Active | New | Normal |  | 2025-05-26 | 25 days | 1900-01-07 08:00 |  |  | 2025-06-27
17 | / | Marketing Phase |  |  | Pre-launch Campaign | Default Workflow | Active | New | Normal |  | 2025-05-26 | 15 days | 1900-01-04 |  |  | 2025-06-13 | 15FS
18 | / | Marketing Phase |  |  | Social Media & Influencer Outreach | Default Workflow | Active | New | Normal |  | 2025-06-16 | 10 days | 1900-01-02 08:00 |  |  | 2025-06-27 | 17FS
19 | / |  |  |  | Launch Phase | Default Workflow | Active | New | Normal |  | 2025-06-30 | 35 days | 1900-01-10 16:00 |  |  | 2025-08-15
20 | / | Launch Phase |  |  | Final Product Adjustments | Default Workflow | Active | New | High |  | 2025-06-30 | 15 days | 1900-01-04 |  |  | 2025-07-18 | 18FS
21 | / | Launch Phase |  |  | Final Testing | Default Workflow | Active | New | High |  | 2025-07-21 | 10 days | 1900-01-02 08:00 |  |  | 2025-08-01 | 20FS
22 | / | Launch Phase |  |  | Launch Preparations | Default Workflow | Active | New | High |  | 2025-08-04 | 10 days | 1900-01-02 08:00 |  |  | 2025-08-15 | 21FS
View:

## RiskMP
Risk Description | Probability (1-5) | Impact (1-5) | Score | Owner (Responsible) | Risk Response | Description of the Response | Action (Prevention) | Monitoring
Delays in Bluetooth module delivery | 3 | 4 | 12 | Project Manager | Mitigation | Work with multiple suppliers and order components early to reduce dependency on one source. | Plan | Meeting
App and glasses integration issues | 2 | 3 | 6 | App Developer | Accept | Conduct early integration testing and use modular coding to address issues quickly.
Battery life limitations | 1 | 1 | 1 | Hardware Engineer | Ignore | Optimize power consumption by selecting efficient components and testing power profiles.
Low user adoption due to complexity | 3 | 2 | 6 | Marketing Specialist | Accept | Focus on user-friendly design and include clear instructions for app and glasses setup.
Budget overruns | 3 | 2 | 6 | Sponsor | Accept | Establish a contingency budget and monitor spending weekly to identify overruns early.
Component defects during prototyping | 3 | 3 | 9 | Hardware Engineer | Mitigation | Test components thoroughly upon delivery and maintain backup inventory for critical parts. | Plan | Meeting
Negative user feedback during testing | 1 | 2 | 2 | Project Manager | Ignore | Use feedback to refine product and adjust non-essential features based on user preferences.
Competitor launching a similar product | 3 | 4 | 12 | Marketing Specialist | Mitigation | Highlight unique features in marketing and accelerate launch timeline to stay competitive. | Plan | Meeting
Regulatory compliance issues | 3 | 4 | 12 | Project Manager | Mitigation | Consult with legal experts early and adhere to all applicable safety and data privacy standards. | Plan | Meeting
Team member unavailability during critical phases | 3 | 3 | 9 | Project Manager | Transfer | Cross-train team members and prepare contingency plans for staff changes or absences. | Ask for help

## RiskMP_PPT
Risk Description | Probability (1-5) | Impact (1-5) | Score | Owner (Responsible) | Risk Response | Action (Prevention) | Monitoring
Delays in Bluetooth module delivery | 3 | 4 | 12 | Project Manager | Mitigation | Plan | Meeting
App and glasses integration issues | 2 | 3 | 6 | App Developer | Accept
Battery life limitations | 1 | 1 | 1 | Hardware Engineer | Ignore
Low user adoption due to complexity | 3 | 2 | 6 | Marketing Specialist | Accept
Budget overruns | 3 | 2 | 6 | Sponsor | Accept
Component defects during prototyping | 3 | 3 | 9 | Hardware Engineer | Mitigation | Plan | Meeting
Negative user feedback during testing | 1 | 2 | 2 | Project Manager | Ignore
Competitor launching a similar product | 3 | 4 | 12 | Marketing Specialist | Mitigation | Plan | Meeting
Regulatory compliance issues | 3 | 4 | 12 | Project Manager | Mitigation | Plan | Meeting
Team member unavailability during critical phases | 3 | 3 | 9 | Project Manager | Transfer | Ask for help

## Meta
Concepts, ideas you want to keep | What it inspires you to put into practice in the situations you experience
The importance of clear communication and using dedicated channels (e.g., WhatsApp). | Build good communication for collaboration in future projects.
Collaboration through structured meetings to brainstorm, align, and divide tasks. | Have regular and GREAT meetings and task delegation, in team projects.
Leveraging diverse expertise from different fields. | Promote profesional diversity in collaboration to gain new perspectives and creative solutions.
Building good relationships with teammates to foster synergy and motivation. | Prioritize team dynamics by incentivating trust and accountability for productive teamwork.
Applying project management concepts (like timelines, task delegation, risk analysis). | Integrate PM methodologies into fields like chemistry, fashion, ML - AI and other industries for better results.

## MetaPPT
Concepts to Keep | Inspiring Actions
Clear communication / channels | Foster collaboration with clear communication
Structured meetings & task delegation | Conduct effective, regular meetings
Leveraging diverse expertise | Embrace diversity for creative solutions
Building team trust & synergy | Build trust for productive teamwork
Applying PM methodologies | Apply PM tools in various industries (chemistry, fashion, AI)